TRILOGY BPO

Architecture Brief — Recruitment Portal

Stack brief · Stage 7 handover · Build approach · Progress log (build day 1)

recruit.trilogybpo.com → Azure SQL: trilogy-hr → hr.trilogybpo.com

How to use this brief Paste into a new chat when starting the recruitment portal build

This document gives the build chat everything it needs: your existing tech stack, the HR system's actual schema and status flow, and a clear statement that the Stage 7 handover should be a same-database SQL write rather than a true external API call — simpler and more reliable given everything lives in trilogy-hr. Because you own both sides and they share one Azure SQL database, you can skip the API-contract negotiation step in the workflow spec. The recruitment portal writes straight into the Employees table.

| Existing tech stack |  | Match this |
| --- | --- | --- |

| Front end | Static HTML / CSS / vanilla JS on GitHub Pages, custom subdomain via Cloudflare DNS-only. No build step, no framework. New repo: recruit.trilogybpo.com. |
| --- | --- |
| Database | Azure SQL (MSSQL), database trilogy-hr. Upsert: IF EXISTS … UPDATE … ELSE INSERT. Recruitment tables added to this same DB so Stage 7 is a same-database write. |
| API layer | Power Automate HTTP-trigger cloud flows. Static pages call flows; flows read/write SQL. Response pattern: body → ResultSets → Table1 with coalesce wrapper for empty results. |
| Auth | Entra ID (MSAL Browser v3, loginRedirect) for staff-facing pages. sessionStorage gates for internal admin pages. Access control checks email against allowlist table in SQL. |
| Email / comms | Microsoft 365 via Power Automate Office 365 Outlook connector. Microsoft Graph for app-level operations. |
| Deployment | Direct file upload to GitHub. No CI/CD pipeline. |

| The HR / onboarding system this must feed |  | Already built |
| --- | --- | --- |

The HR portal (hr.trilogybpo.com) and onboarding pipeline already exist, running on an Employees table in trilogy-hr with the status flow below:

| Offer Sent | Offer Signed | Contract Sent | Contract Signed | To Be Onboarded | Active |
| --- | --- | --- | --- | --- | --- |

Key Employees fields the onboarding system relies on:

- EmployeeID (PK, format TBP-YYYY-RXXXXXX)

- FirstName, LastName, PreferredName, IDNumber, Gender, DateOfBirth

- Mobile, PersonalEmail, WorkEmail, Address

- JobTitle, Campaign, Salary, StartDate, ReportsTo, ReportsToEmail, Status

- Related tables: BankingDetails, EmergencyContacts, ITOnboarding (queue)

| Stage 7 — The critical integration |  | HR handover |
| --- | --- | --- |

Handover principle: same-database SQL write No re-keying. No cross-system sync. No API contract negotiation.

When HR approves a completed candidate file, a Power Automate flow writes directly into the Employees table and related tables (BankingDetails, EmergencyContacts) in the shared trilogy-hr database. Because both portals share the same Azure SQL instance, no external API push is required. Assessment scores (Pivotal Talent) and BGV status (iFacts) must be stored against the employee record so the full candidate history follows them into onboarding.

Field mapping — Recruitment → HR Employees

| Recruitment field | HR Employees field | Notes |
| --- | --- | --- |
| Candidate.FirstName | Employees.FirstName | Direct map |
| Candidate.LastName | Employees.LastName | Direct map |
| Candidate.PreferredName | Employees.PreferredName | Direct map |
| Candidate.IDNumber | Employees.IDNumber | Direct map |
| Candidate.Gender | Employees.Gender | Direct map |
| Candidate.DateOfBirth | Employees.DateOfBirth | Direct map |
| Candidate.Mobile | Employees.Mobile | Direct map |
| Candidate.PersonalEmail | Employees.PersonalEmail | Direct map |
| — (generated) | Employees.WorkEmail | Create @trilogybpo.com address at handover |
| Application.JobTitle | Employees.JobTitle | From job posting / campaign config |
| Application.CampaignCode | Employees.Campaign | Direct map |
| Application.OfferedSalary | Employees.Salary | Set at offer stage |
| Application.StartDate | Employees.StartDate | Confirmed at offer sign |
| Application.ReportsTo | Employees.ReportsTo / ReportsToEmail | From campaign config or recruiter assignment |
| — (set by flow) | Employees.Status | Set to 'Offer Sent' at handover trigger |
| — (auto-generate) | Employees.EmployeeID | Generate TBP-YYYY-RXXXXXX at insert time |
| Candidate.BankingDetails | BankingDetails table | Insert linked record(s) |
| Candidate.EmergencyContacts | EmergencyContacts table | Insert linked record(s) |
| Assessment.PivotalScores | RecruitmentHistory table | Scores + LOB stored against EmployeeID |
| BGV.iFactsStatus | RecruitmentHistory table | BGV outcome; flag visible to HR |

| Third-party integrations |  | Wire in |
| --- | --- | --- |

| ⚡ | Pivotal Talent Stage 3 — Assessments | Obtain API credentials. Confirm webhook payload structure, auth method, score field names, and pass/fail flag format. LOB routing driven by campaign code. Assessment link delivered via email + WhatsApp. |
| --- | --- | --- |
| 🔍 | iFacts Stage 5 — Background checks | Obtain API docs and check package codes per role. Confirm result delivery method (webhook vs polling). CRITICAL: flagged results must route to HR for human decision — platform must NOT auto-reject. |
| 💬 | WhatsApp Business API All stages — comms | Every notification delivered in parallel via email AND WhatsApp. Candidate phone captured at Stage 1 is used throughout the full pipeline. |

| Compliance requirements |  | POPIA · BCEA · EEA |
| --- | --- | --- |

✓  POPIA — candidate consent captured and timestamped at submission, stored against candidate record

✓  BCEA — all required personal data fields captured (name, DOB, address, NOK, banking details)

✓  EEA Act 55 — EE classification fields (race, gender, disability, occupational level) auto-mapped to report categories

✓  iFacts BGV — flagged results routed to HR for human decision; no auto-reject permitted

✓  POPIA — employee file data encrypted, access-controlled, and audit-logged throughout

✓  e-Signature on employment contracts captured and stored against the employee file

✓  Audit trail on all status changes, approvals, and the Stage 7 handover trigger event

| Recommended build approach |  | How to sequence this |
| --- | --- | --- |

The core principle: build the spine first, then hang the complexity off it Start with what you control 100%. Defer what depends on third parties.

The seven-stage workflow spec is comprehensive, but it mixes two very different things: things you can build right now (your own SQL + Power Automate + static pages) and things that depend on third parties (Pivotal Talent webhooks, iFacts API, WhatsApp Business API). Build the spine first. Stub the integrations. Wire them in when you have the credentials and documentation. The Stage 7 handover is the most important thing to get right architecturally — everything else is in service of it. So the SQL schema and the handover flow should be designed on day one, even if the portal pages come later.

Build phases

| P1 | Foundation — Schema + Core Data Layer Week 1 · Purely internal, no third-party dependencies |
| --- | --- |

What you're doing Setting up everything you own and control 100%

Design and deploy all recruitment SQL tables in trilogy-hr. This is the most important architectural decision in the project — get the schema right here and the rest flows easily. Tables to create: - Candidates — core personal data, EE fields, POPIA consent timestamp, status - Applications — links candidate to campaign/LOB, salary, start date, ReportsTo - Assessments — Pivotal Talent scores per LOB, pass/fail flag, received timestamp - BGV — iFacts reference, check types, status (Clear/Flagged/Pending), HR decision - Documents — uploaded file references (ID, matric, CV, IT150, signed contract) - InterviewNotes — structured feedback from HR rep + ops manager, joint outcome - RecruitmentAuditLog — every status change, who triggered it, timestamp - RecruitmentHistory — links CandidateID to EmployeeID post-handover Key schema decision: CandidateID is a recruitment-portal-only identifier. EmployeeID (TBP-YYYY-RXXXXXX format) is only generated at the Stage 7 handover write. Don't conflate the two — they live in different tables with a foreign key linking them post-handover.

| P2 | Recruiter-facing portal + Application intake Weeks 1–2 · Internal tools first |
| --- | --- |

What you're building The recruiter dashboard and the candidate application form — the two ends of Stage 1

Build the recruiter-facing admin portal (accessible at recruit.trilogybpo.com, gated by sessionStorage auth to match your HR portal pattern). This is your team's primary interface. Build it before the candidate-facing pages — you'll use it to test every subsequent stage. Recruiter portal pages: - Dashboard — pipeline overview, stage counts, recent activity - Campaign manager — create campaigns, generate unique URLs and QR codes per LOB - Candidate list — sortable, filterable, bulk-select for shortlisting - Candidate detail view — full file, status history, documents, scores, BGV - Interview scheduler — slot management, panel assignment Candidate application form (public-facing): - Mobile-first, no auth required, URL param carries campaign/LOB code - Captures: name, DOB, ID number, contact details, current employment status - POPIA consent checkbox with timestamped acceptance stored to SQL immediately - Document upload: certified ID/passport, matric certificate, CV Power Automate flows needed: SubmitApplication (creates Candidates + Applications rows), GetCandidateList, GetCandidateDetail, UpdateCandidateStatus, GetCampaignList, CreateCampaign.

| P3 | EE Data Collection + Shortlisting Week 2 |
| --- | --- |

What you're building Stage 2 data capture and Stage 4 recruiter shortlist workflow

After application submission, candidates who pass the initial screen are prompted to complete their EE profile. This is a second form, linked from the confirmation email. It feeds the EE classification fields required for the Employment Equity Act report. EE data form captures: - Race, gender (confirm), disability status, highest qualification - Occupational level (pre-mapped from job posting), previously disadvantaged indicator - Auto-classification to EEA Act 55 report categories on save Shortlist view (Stage 4): - Ranked list view — sortable by score once assessments are wired in (stub score column for now) - EE category breakdown per shortlist — visible to recruiter before advancing candidates - Bulk-select + advance to interview stage with single action Note: Build the shortlist view with a stub score column. When Pivotal Talent is wired in (Phase 5), the column populates automatically — the view doesn't need to change.

| P4 | Stage 7 Handover Flow — THE CRITICAL BUILD Week 2–3 · Build this before the interview module |
| --- | --- |

Why build Stage 7 before Stage 5 and 6? This is the integration point with your existing HR portal — get it right early

Counter-intuitive but important: build the handover flow before you build the interview and BGV modules. Here's why: every stage of the recruitment pipeline is ultimately in service of producing a correct Employees row. If you build Stages 5 and 6 first and then discover the handover mapping is wrong, you may need to rework data structures. Build the destination first, then work backwards. The handover flow does: - Triggered by HR approval action on candidate detail view - Generates EmployeeID in TBP-YYYY-RXXXXXX format - Writes to Employees table using IF EXISTS … UPDATE … ELSE INSERT pattern - Writes linked BankingDetails and EmergencyContacts rows - Writes RecruitmentHistory row linking CandidateID to new EmployeeID - Sets Employees.Status = 'Offer Sent' (entry point to existing onboarding pipeline) - Triggers welcome email + WhatsApp to candidate with onboarding portal link - Writes to RecruitmentAuditLog: who approved, timestamp, EmployeeID created Test this with a dummy candidate against your real trilogy-hr database before building Stages 5 and 6. Confirm the new Employees row appears correctly in your existing HR portal (hr.trilogybpo.com) and enters the onboarding pipeline at the right status.

| P5 | Pivotal Talent integration (assessments) Week 3 · Requires credentials from Pivotal Talent |
| --- | --- |

What you're wiring in Stage 3 — automated psychometric assessments

This phase is gated on getting API credentials and webhook documentation from Pivotal Talent. Start the conversation with them before you finish Phase 2 so you're not waiting when you get here. What needs confirming with Pivotal Talent before build: - API endpoint + authentication method (API key, OAuth?) - How LOB routing works — does campaign code map to a Pivotal assessment battery ID? - Webhook payload structure — what fields come back, what does the pass/fail flag look like? - Webhook auth — how does Pivotal sign its callbacks so you know they're genuine? Power Automate flows needed: - TriggerPivotalAssessment — called after application submission, passes candidate + LOB code - ReceivePivotalWebhook — HTTP-trigger flow that receives callback, writes to Assessments table, updates candidate status Stub approach while waiting: build a manual "Enter score" input on the candidate detail view. Recruiter types the score manually. When the webhook flow is wired in, the manual input becomes read-only and auto-populates instead. No rework of the UI needed.

| P6 | iFacts integration + Document completion Week 3–4 · Requires iFacts API docs |
| --- | --- |

What you're wiring in Stage 5 — background checks and candidate self-service document forms

iFacts is the other external dependency. Same approach as Pivotal Talent: start the conversation early, build with stubs, wire in when docs are available. iFacts integration: - TriggeriFacts flow — submits ID number + personal details on verbal offer, stores reference number - ReceiveiFacts callback — ingests results, writes to BGV table, sets Clear/Flagged/Pending - CRITICAL: flagged result triggers HR notification, shows review required badge — no auto-reject logic anywhere in the flow Candidate self-service forms (no third-party dependency — build now): - Banking details form — bank name, account number, account type, branch code - SARS IT150 upload — document storage, tax number extracted and stored - Address + next of kin form — physical/postal address, primary + secondary NOK These self-service forms are candidate-facing, tokenised links (no login required). Token generated on verbal offer, stored in SQL, expires after 7 days. Same pattern as your existing onboarding document collection.

| P7 | WhatsApp Business API + Interview module Week 4 · Wire in comms layer and complete Stage 4/6 flows |
| --- | --- |

What you're completing Parallel comms channel and the interview management module

WhatsApp Business API requires a Meta Business account, a verified phone number, and pre-approved message templates. This takes time to set up — apply for access before you start Phase 5. Email-only delivery works fine while WhatsApp approval is pending; the flow architecture just adds WhatsApp as a second action in every notification flow. WhatsApp integration points: - Application confirmation (Stage 1) - Assessment link delivery (Stage 3) - Assessment result notification — pass or regret (Stage 3) - Interview booking link (Stage 4) - Verbal offer notification (Stage 4) - Document collection links — banking, IT150, NOK (Stage 5) - Onboarding welcome message with portal link (Stage 7) Interview module (Stage 4 completion): - Slot management — recruiter creates available interview windows - Booking link — candidate selects from available slots, confirmation auto-sent - Structured feedback form — separate views for HR rep and ops manager - Joint outcome capture — both parties must submit before decision is recorded Calendar invite delivery: Use Power Automate's Office 365 Outlook connector to send .ics calendar invites to candidate, HR rep, and ops manager. This is native to your stack — no third-party calendar integration needed.

| P8 | Contract generation + e-signature (Stage 6) Week 4–5 · Final pre-handover module |
| --- | --- |

What you're completing Auto-populated employment contracts and digital signature capture

The contract and offer letter are auto-generated from the candidate record using a Word template (mail-merge style). The platform generates the document, sends it for digital signature, and stores the signed copy. HR rep and ops manager are cc'd on the signed version. Key decisions to make before building: - e-Signature provider: DocuSign, Adobe Sign, or HelloSign — all have Power Automate connectors. Alternatively, a simple "click to confirm" with IP + timestamp capture works for basic BCEA compliance without a third-party tool. - Contract template: a Word doc (.docx) with merge fields. Power Automate fills the fields and converts to PDF for delivery. Once the signed contract is on file and HR approves the complete record, the Stage 7 handover flow (built in Phase 4) is triggered. Everything downstream of this is already built and tested.

| Phase dependency summary |  | What's gated on what |
| --- | --- | --- |

| Phase | Deliverable | Depends on | Approx. time |
| --- | --- | --- | --- |
| P1 — Schema | SQL tables (all recruitment data) | Nothing — start here | 2–3 days |
| P2 — Portal | Recruiter dashboard + candidate application form | P1 complete | 3–4 days |
| P3 — EE + Shortlist | EE data capture + shortlist view | P2 complete | 2 days |
| P4 — Stage 7 flow | Handover to HR Employees table | P1 + P2 tested | 2 days |
| P5 — Pivotal | Assessment trigger + webhook ingestion | P2 + Pivotal creds | 2–3 days |
| P6 — iFacts + docs | BGV flow + candidate self-service forms | P2 + iFacts API docs | 3 days |
| P7 — WhatsApp + interviews | Comms layer + interview module | P2 + Meta approval | 3–4 days |
| P8 — Contracts | Contract generation + e-signature | P3 + P6 complete | 3–4 days |

| Key risks & mitigations |  | Know before you start |
| --- | --- | --- |

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Pivotal Talent API / webhook docs delayed | High | Start conversations immediately. Build manual score-entry stub — portal is fully usable without the integration. |
| iFacts API access / check package configuration | High | Same approach — stub BGV status field, HR enters manually until API is live. Never blocks the pipeline. |
| WhatsApp Business API approval (Meta) | Medium | Apply for access in Week 1. Email-only delivery is full fallback — every comms flow sends email first, WhatsApp is additive. |
| e-Signature provider decision not made | Medium | Default to click-to-confirm with IP + timestamp for initial launch. Swap for DocuSign/Adobe Sign post-launch without schema changes. |
| Schema design errors found late | High | Phase 4 (Stage 7 flow) forces a real end-to-end test early. Any schema issues surface before the full portal is built. |
| Document storage (uploaded files) | Low | Recommend SharePoint / OneDrive via Graph API — matches your existing stack. Azure Blob Storage is the alternative. Decide in Phase 1. |

| Key decisions to make before starting |  | Confirm before build |
| --- | --- | --- |

| Decision / assumption | Our approach | Alternative |
| --- | --- | --- |
| Document storage for uploads (ID, CV, matric, contracts) | SharePoint / OneDrive via Microsoft Graph — already in your stack | Azure Blob Storage — cleaner but another service to manage |
| e-Signature for employment contracts | Click-to-confirm (IP + timestamp) — no third-party cost, BCEA-compliant for basic use | DocuSign / Adobe Sign Power Automate connector — more robust, adds cost |
| WhatsApp Business API provider | Direct Meta Cloud API — most control, lower per-message cost | 360dialog or Twilio as middleware — faster to set up, easier webhook handling |
| Candidate portal auth (self-service forms) | Tokenised links (no login) — token in SQL, expires after 7 days. Simpler for candidates. | OTP via SMS or email — more secure but adds friction in a high-volume recruitment context |
| Interview slot management | Build simple slot table in SQL, booking flow in Power Automate — no third-party | Calendly / Microsoft Bookings — faster to deploy but harder to customise for joint panel requirements |
| QR code generation for campaigns | Generate QR on the fly in the browser (qr.js library) — no backend needed, encodes unique campaign URL | Server-side generation and storage — adds complexity with no meaningful benefit |

| What to have ready on build day |  | Tomorrow's starting point |
| --- | --- | --- |

Checklist before opening the build chat

Confirmed decisions: ○ Document storage confirmed: SharePoint/OneDrive via Graph OR Azure Blob ○ e-Signature approach confirmed: click-to-confirm OR third-party provider chosen ○ WhatsApp API route confirmed: direct Meta OR middleware provider In progress (start now, don't wait): ○ Email sent to Pivotal Talent requesting API credentials and webhook documentation ○ Email sent to iFacts requesting API documentation and check package codes for your role types ○ Meta Business account created and WhatsApp Business API application submitted Ready to build (Phase 1 on day 1): ✓ Access to trilogy-hr Azure SQL confirmed ✓ Power Automate environment with HTTP trigger capability confirmed ✓ New GitHub repo (recruit.trilogybpo.com) created ✓ Cloudflare DNS subdomain record created for recruit.trilogybpo.com

| Build progress log |  | Status as of build day 1 |
| --- | --- | --- |

Where we are Phase 1 complete · Phase 2 in progress

The database foundation is built and verified against the live trilogy-hr instance. The recruiter-facing portal shell (dashboard + campaign manager) is built and running in stub mode. Power Automate flows are the next step to make the pages live. A key structural decision was made and applied on day one: campaigns and roles were split into separate tables, because a BPO campaign recruits many role types (Agents, Team Leaders, Ops Managers, support staff) — not a single role. Each role now carries its own application URL, salary band, assessment battery, and advert content.

| P1 | Foundation — Schema + Core Data Layer COMPLETE · verified against live database |
| --- | --- |

Deployed to trilogy-hr:

- 15 tables (all prefixed Rec_) — zero collision with existing HR tables

- Rec_Campaigns, Rec_Roles, Rec_Candidates, Rec_Applications, Rec_Documents, Rec_Assessments

- Rec_InterviewSlots, Rec_Interviews, Rec_BGV, Rec_BankingDetails, Rec_EmergencyContacts

- Rec_CandidateTokens, Rec_CommLog, Rec_AuditLog, Rec_RecruitmentHistory

- 3 views: Rec_vw_ApplicationPipeline, Rec_vw_DashboardCounts, Rec_vw_RoleCounts

- 6 stored procedures (see below)

Stored procedures deployed

| Procedure | Purpose |
| --- | --- |
| Rec_CreateCampaign2 | Creates a campaign (engagement). 6 params: code, title, client, LOB, department, created-by |
| Rec_CreateRole | Creates a role under a campaign. Full role config incl. salary band, assessment, advert fields |
| Rec_UpsertCandidate | Insert-or-update a candidate by ID number (called on application submit) |
| Rec_UpdateApplicationStatus | Changes application status + writes an audit log row in one call |
| Rec_Stage7Handover | THE critical one. Writes approved candidate into the HR Employees table + BankingDetails, EmergencyContacts, ITOnboarding. Aligned to the real HR schema. Transaction-wrapped. |
| Rec_ValidateToken | Validates a candidate self-service token (used / expired / valid) |

Stage 7 handover — schema alignment notes Discovered by inspecting the live HR tables — baked into Rec_Stage7Handover

- Employees.EmployeeID is NVARCHAR(40), not IDENTITY — the proc generates TBP-YYYY-RXXXXXX and inserts it - Employees.Address is a single field — recruitment address parts are concatenated on handover - Employees.Disability is a BIT + DisabilityDetails text — mapped from the recruitment status field - Employees.FullName and Initials are derived and populated by the proc - BankingDetails uses AccountHolder (not AccountHolderName) and has a BranchName column - EmergencyContacts uses ContactType + IsPrimary (not ContactOrder); Address is a single field - ITOnboarding.EmployeeID is VARCHAR(50) — cast on insert; an IT queue row is created at handover

| P2 | Recruiter portal + Campaign manager IN PROGRESS · pages built, flows next |
| --- | --- |

Pages built (static HTML, GitHub Pages):

- index.html — recruiter dashboard. Hero stats, live pipeline bar, "needs attention" cards, 8-module grid, active campaigns with progress bars, recent activity feed

- campaigns.html — two-level campaign manager. Create campaign (engagement), then add roles below with quick-pick buttons for standard BPO roles (Agent, SME, TL, OM, CCM, OD + support: Recruiter, Trainer, HR, MIS, IT, QA) plus a custom option

- Both match the HR portal look exactly: navy/green, Montserrat headings, trilogy-logo.png, sessionStorage login gate (same credentials as HR portal)

- Each role auto-generates its own application URL and QR code

- Both pages run in stub mode until flow URLs are pasted in — fully clickable for testing now

Key decisions confirmed on build day:

✓  Document storage: SharePoint / OneDrive via Microsoft Graph

✓  e-Signature: click-to-confirm (IP + timestamp captured) — no third-party provider

✓  Candidate portal auth: tokenised links, expire after 7 days

✓  Campaign codes widened to NVARCHAR(40) to fit the TBP-LOB-YYYY-XXXX format

Next up — four Power Automate flows:

| Flow | Calls / queries | Powers |
| --- | --- | --- |
| CreateCampaign2 | Rec_CreateCampaign2 | Campaign manager — create campaign |
| GetCampaigns | Rec_Campaigns / dashboard query | Campaign dropdown + dashboard |
| CreateRole | Rec_CreateRole | Campaign manager — add role |
| GetRoles | Rec_vw_RoleCounts | Roles list per campaign |

Power Automate build notes (learned on day 1)

- Server name: trilogy-hr.database.windows.net · Database: trilogy-hr (enter directly — PA has no dropdown) - Map stored-proc parameters using the expression editor: triggerBody()?['FieldName'] — more reliable than the dynamic content picker, which can mangle union-type JSON schemas - Keep trigger JSON schema fields as plain strings — avoid ["string","null"] union types, they break the dynamic content list - After altering a stored proc, re-select it in the Execute stored procedure (V2) action so PA re-reads the parameter metadata (it caches the old signature) - SQL connector validates parameter lengths before hitting SQL — proc parameter lengths must match the column widths exactly - Pages parse responses defensively: read as text, then unwrap {ResultSets:{Table1:[...]}} ¦ {Table1:[...]} ¦ [...] ¦ {...}